## Sheet1
Task Details | Initial Effort Estimate (hrs) | New Estimates of Effort remaining at end of | [12 empty] | Status
|  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Create Angular components for patient registration and login | 1 | New Estimates of Effort remaining at end of Day 1: 1; New Estimates of Effort remaining at end of Day 2: 0 | Complete
Implement reactive form validations in Angular | 2 | New Estimates of Effort remaining at end of Day 1: 2; New Estimates of Effort remaining at end of Day 2: 1; New Estimates of Effort remaining at end of Day 3: 0 | Complete
Develop Spring Boot REST APIs for registration and login | 3 | New Estimates of Effort remaining at end of Day 1: 3; New Estimates of Effort remaining at end of Day 2: 2; New Estimates of Effort remaining at end of Day 3: 1; New Estimates of Effort remaining at end of Day 4: 0 | Complete
Implement authentication logic in Spring Boot | 3 | New Estimates of Effort remaining at end of Day 1: 0; New Estimates of Effort remaining at end of Day 2: 0; New Estimates of Effort remaining at end of Day 3: 0; New Estimates of Effort remaining at end of Day 4: 0; New Estimates of Effort remaining at end of Day 5: 1; New Estimates of Effort remaining at end of Day 6: 2; New Estimates of Effort remaining at end of Day 7: 0 | Complete
Persist patient data using JPA and MySQL | 3 | New Estimates of Effort remaining at end of Day 1: 0; New Estimates of Effort remaining at end of Day 2: 2; New Estimates of Effort remaining at end of Day 3: 1; New Estimates of Effort remaining at end of Day 4: 0 | Complete
Design homepage layout using Angular | 1 | New Estimates of Effort remaining at end of Day 1: 1; New Estimates of Effort remaining at end of Day 2: 0 | Complete
Create reusable Angular components for services display | 1 | New Estimates of Effort remaining at end of Day 1: 1; New Estimates of Effort remaining at end of Day 2: 0 | Complete
Configure Angular routing for navigation | 2 | New Estimates of Effort remaining at end of Day 1: 0; New Estimates of Effort remaining at end of Day 2: 1; New Estimates of Effort remaining at end of Day 3: 1; New Estimates of Effort remaining at end of Day 4: 0 | Complete
Fetch dynamic data using REST APIs | 2 | New Estimates of Effort remaining at end of Day 1: 0; New Estimates of Effort remaining at end of Day 2: 0; New Estimates of Effort remaining at end of Day 3: 1; New Estimates of Effort remaining at end of Day 4: 1; New Estimates of Effort remaining at end of Day 5: 0 | Complete
Test homepage responsiveness and UI | 2 | New Estimates of Effort remaining at end of Day 1: 1; New Estimates of Effort remaining at end of Day 2: 1; New Estimates of Effort remaining at end of Day 3: 0 | Complete
Create Angular appointment booking component | 2 | [13 empty] | Complete
Fetch doctor specialties using Spring Boot APIs | 2 | [13 empty] | Complete
Display available doctors based on filters | 2 | [13 empty] | Complete
Implement appointment booking REST API | 4 | [13 empty] | Complete
Save appointment data using JPA | 2 | [13 empty] | Complete
Generate appointment confirmation response | 1 | [13 empty] | Complete
Create Angular payment component UI | 2 | [13 empty] | Complete
Implement static card payment form | 1 | [13 empty] | Complete
Validate payment inputs on frontend | 2 | [13 empty] | Complete
Develop payment confirmation API in Spring Boot | 3 | [13 empty] | Complete
Store payment details in database | 2 | [13 empty] | Complete
Display patient appointments using Angular | 2 | [13 empty] | Complete
Implement reschedule appointment UI | 2 | [13 empty] | Complete
Implement cancel appointment functionality | 2 | [13 empty] | Complete
Update appointment status via REST API | 3 | [13 empty] | Complete
Persist changes in database | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | [5 empty] | Complete
Create Angular admin login component | 1 | [13 empty] | Complete | bar: New Estimates of Effort remaining at end of Day 6
Implement static admin authentication logic | 1 | [13 empty] | Complete
Secure admin routes using guards | 3 | [13 empty] | Complete
Create admin session handling | 3 | [13 empty] | Complete
Redirect admin to dashboard | 2 | [13 empty] | Complete
Create Angular form for doctor management | 1 | [13 empty] | Complete
Develop REST APIs for doctor CRUD operations | 2 | [13 empty] | Complete
Generate doctor login credentials | 3 | [13 empty] | Complete
Persist doctor data using JPA | 2 | [13 empty] | Complete
Validate doctor inputs | 1 | [13 empty] | Complete
Display all appointments in Angular table | 1
Fetch appointment data via REST API | 2
Update appointment status functionality | 3
Delete appointment records | 2
Sync changes with database | 1
Create appointment search UI in Angular | 1
Implement filter logic in frontend | 1
Develop search APIs in Spring Boot | 2
Optimize database queries | 3
Display filtered appointment results | 2
Create Angular complaint registration component | 2
Validate complaint form inputs | 3
Develop REST API for complaint submission | 3
Store complaint details in database | 2
Notify admin of new complaint | 2
Display complaint list in Angular | 1
Fetch complaint status via REST API | 1
Show real-time complaint status updates | 1
Handle pending and resolved complaints | 2
Test complaint tracking flow | 1
Display all complaints in admin dashboard | 1
Update complaint status via REST API | 2
Add resolution remarks | 3
Notify patient about resolution | 1
116